## Feuille1
CR	Title	Description	Owner	Reviewer	Status	GSMA status
001	Android API	- Missing classes GeolocMessage and Geoloc. / - New RCS 5.2 syntax for feature tag extensions. / - New automata flag in capabilities. / - Missing geoloc methods in the chat service. / - Missing configuration settings for the geoloc service. / - New method to return the service version. / - Remove the altitude in geoloc info. / - Missing chat ID in the file transfer Intent. / - Remove the method transferFileToGroup in the FT API.	JMA	KK	Ready for GSMA review
002	MM session API	- Internalize the media layer in the API with MSRP support only. / - Remove any SDP parameters in the API definition. / - Rename package to “com.gsma.services.rcs.session”. / - Add new service ID syntax.	JMA	KK	Ready for GSMA review
003	Application identification	- Add an application ID to identify the application using the service API. / - Add a method to indicate that it’s an app-to-app service	JMA	KK	Ready for GSMA review
004	URI for filenames	- Use an Android Uri instead of a String for filenames	JMA	KK	Ready for GSMA review
005	Delete methods	- Add method to delete logs (chat, message, FT, CSH)	KK	PL	Ready for GSMA review
006	Missing Capabilities	- Add a file transfer thumbnail capabilities. / - Add a timestamp	JMA	KK	Ready for GSMA review
007	Service API	- Add an Intent when service is UP. / - Add methods for service provisioning	JMA	KK	Ready for GSMA review
008	Messaging API	- Few callbacks replaced by intents / - Added intents and/or intent parameters / - isPauseSupported on FileTransfer api / - Resend file- or text-message (one2one only)	KK	JMA/PL	Discussions not finalized yet
009	Reason code	- Add a reason code associated to a failure or an aborted status in DB / - Add a reason code in the aborted event listeners.	JMA	KK	To be updated by Sony. Add values for reason codes and callbacks
010	Participant	- Add method to get participant state / - Add listener to get participant state changes	PL	KK	Ready for GSMA review
011	Send message	- Queuing / - Dequeuing / - Global listeners / - Hide rejoin / restart	KK	JMA/PL	In progress of analysing and writing
012	Read/Displayed/Delivered	- DeliveryInfo provider / - Separate read/unread field / - Delivery status callbacks / - chatID for file transfers / - msgID for file transfers	KK	JMA/PL	In progress of analysing and writing
013	Message search	- Replace BLOB by TEXT for chat messages / - parse content via utility method	PL	KK	Ready for GSMA review
014	Contact Service Utilities	- Add methods to format contact and check validity	KK	JMA/PL	In progress of analysing and writing
015	RCS settings	- Add RCS settings / (add comments for MaxMessageLength in chat + GC)	PL	KK	In progress of analysing and writing
016	Display Name	- Add method to get the display name associated to a contact. / - Add column in contact DB	JMA/PL	KK	Currently in review
017	Use case capabilities	- define methods to check capabilities depending on Use Cases	KK	JMA/PL	Not started yet
018	Get/open/accept for chat/gc/ft		KK	JMA/PL	Not started yet
019	Undelivered messages				Discussions not finalized yet
020	Merged cursors/EventLogProvider				Discussions not finalized yet
TBD	Exception handling				Purposly postponed until last