## Feuille1
CR	Title	Description	Owner	Reviewer	Status	GSMA / status	Implementation / GIT branch	Implementation status / (implemented | integrated)
001	Android API	- Missing classes GeolocMessage and Geoloc. / - New RCS 5.2 syntax for feature tag extensions / - New automata flag in capabilities / - Missing geoloc methods in the chat service / - Missing configuration settings for the geoloc service / - Remove altitude / - etc	JMA	KK	Ready for GSMA review	Agreed
002	MM session API	- Internalize the media layer in the API with MSRP support only. / - Remove any SDP parameters in the API definition. / - Rename package to “com.gsma.services.rcs.session”. / - Add new service ID syntax.	JMA	KK	Ready for GSMA review	R3 to be reviewed	cr002
003	Application identification	- Add an application ID to identify the application using the service API. / - Add a method to indicate that it’s an app-to-app service	JMA	KK	To be completed by adding also appId in database.
004	URI for filenames	- Use an Android Uri instead of a String for filenames	JMA	KK	Ready for GSMA review		internal Sony branch
005	Delete methods	- Add method to delete logs (chat, message, FT, CSH)	KK	PL	Ready for GSMA review
006	Missing Capabilities	- Add a timestamp	JMA	KK	Ready for GSMA review
007	Service API	- Add an Intent when service is UP. / - Add methods for service provisioning	JMA	KK	Ready for GSMA review	Agreed	integration	integrated
008	Messaging API	- isPauseSupported on FileTransfer api / - Resend file or text-message (one2one only)	KK	JMA/PL	Ready for GSMA review
009	Reason code	- Add a reason code associated to a failure or an aborted status in DB / - Add a reason code in the aborted event listeners.	JMA/KK	JMA/PL	Ready for GSMA review
010	Participant	- Add method to get participant state / - Add listener to get participant state changes	PL	KK/JMA	Ready for GSMA review		cr10-ice91	implemented
011	Global listener	- Add global listener for queueing, for multidevice, for delivery report simplification in general	KK	JMA/PL	Ready for GSMA review
012	Read/Displayed/Delivered	- DeliveryInfo provider / - Separate read/unread field / - Delivery status callbacks / - chatID for file transfers / - msgID for file transfers	KK	JMA/PL	Ready for GSMA review		internal Sony branch
013	Message search	- Replace BLOB by TEXT for chat messages / - Parse content via utility method	PL	KK	Ready for GSMA review		integration	integrated
014	Contact Service Utilities	- Add methods to format contact and check validity	KK	JMA	Ready for GSMA review
015	RCS settings	- Add RCS settings / (add comments for MaxMessageLength in chat + GC)	PL	KK	Ready for GSMA review
016	Display Name	- Add method to get the display name associated to a contact. / - Add column in contact DB	JMA/PL	KK	Ready for GSMA review
017	Use case capabilities	- Define methods to check capabilities depending on Use Cases	KK	JMA/PL	To be reviewed
018	Messaging enhancements	- Queuing (chat and file transfer) / - Dequeuing / - Hide rejoin / restart	KK	JMA/PL	Ready for GSMA review		internal Sony branch / quit-gc	implemented
019	Undelivered messages	- Manage undelivered messages and file transfers	KK	JMA/PL	To be reviewed
020	Merged cursors / /EventLogProvider	- Pseudo content provider	KK	JMA/PL	To be done		internal Sony branch
021	Intents	- Pass only ID in Intent parameter and then use the database provider to extract informations. / - Add new Intents and update some existing ones.	KK	JMA/PL	To be reviewed
022	Contact ID object	- Define an object ContactId instead of using String for robutness	KK	JMA/PL	To be done		cr024-ice69
023	JoynUtils	- Rename JoynClient by JoynService	JMA	KK	Ready for GSMA review
024	Thumbnail	- Use a boolean instead of a filepath for thumbnail	JMA	KK	Ready for GSMA review
TBD	Exception handling				Purposly postponed until last CR