## Feuille1
CR	Title	Description	Status	GSMA / status	CR document	Implementation
001	Android API	- Missing classes GeolocMessage and Geoloc. / - New RCS 5.2 syntax for feature tag extensions / - New automata flag in capabilities / - Missing geoloc methods in the chat service / - Missing configuration settings for the geoloc service / - Remove altitude / - etc	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR001_Android_API_R3.doc	integrated
002	MM session API	- Internalize the media layer in the API with MSRP support only. / - Remove any SDP parameters in the API definition. / - Rename package to “com.gsma.services.rcs.session”. / - Add new service ID syntax.	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR002_Multimedia_Session_API_R4.doc	integrated
003	Application identification	- Add an application ID to identify the application using the service API. / - Add a method to indicate that it’s an app-to-app service	Moved to Crane			postponed
004	URI for filenames	- Use an Android Uri instead of a String for filenames	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR004_URI_filenames.doc	integrated
005	Delete methods	- Add method to delete logs (chat, message, FT, CSH)	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR005_Delete_methods.doc	in progress SONY
006	Missing Capabilities	- Add a timestamp	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR006_Missing_capabilities_R2.doc	in progress Orange
007	Service API	- Add an Intent when service is UP. / - Add methods for service provisioning	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR007_Service_API_R2.doc	integrated
008	Messaging API	- isPauseSupported on FileTransfer api / - Resend file or text-message (one2one only)	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR008_Messaging_API.doc	in progress SONY
009	Reason code	- Add a reason code associated to a failure or an aborted status in DB / - Add a reason code in the aborted event listeners.	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR009_Reason_code_R3.doc	in progress SONY
010	Participant	- Add method to get participant state / - Add listener to get participant state changes	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR010_Participant.doc	integrated
011	Global listener	- Add global listener for queueing, for multidevice, for delivery report simplification in general	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR011_Global_Listeners_R2.doc	in progress SONY
012	Read/Displayed/Delivered	- DeliveryInfo provider / - Separate read/unread field / - Delivery status callbacks / - chatID for file transfers / - msgID for file transfers	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR012_DeliveryInfo_markAsRead_R3.doc	integrated
013	Message search	- Replace BLOB by TEXT for chat messages / - Parse content via utility method	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR013_MessageSearch.doc	integrated
014	Contact Service Utilities	- Add methods to format contact and check validity	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR014_Contacts_utils_R2.doc	integrated
015	RCS settings	- Add RCS settings / (add comments for MaxMessageLength in chat + GC)	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR015_RcsSettings_R2.doc	integrated
016	Display Name	- Add method to get the display name associated to a contact. / - Add column in contact DB	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR016_Displayname.doc
017	Use case capabilities	- Define methods to check capabilities depending on Use Cases	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR017_Usecase_capabilities.doc
018	Messaging enhancements	- Queuing (chat and file transfer) / - Dequeuing / - Hide rejoin / restart	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR018_Messaging_enhancements_R2.doc	in progress SONY
019	Undelivered messages	- Manage undelivered messages and file transfers	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR019_Undelivered_messages_R2.doc	in progress SONY
020	Merged cursors / /EventLogProvider	- Pseudo content provider	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR020_Merged_cursors.doc	in progress SONY
021	Intents	- Pass only ID in Intent parameter and then use the database provider to extract informations. / - Add new Intents and update some existing ones.	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR021_Intents.doc
022	Contact ID object	- Define an object ContactId instead of using String for robutness	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR022_ContactID_R3.doc	integrated
023	JoynUtils	- Rename JoynClient by JoynService	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR023_JoynUtils.doc	integrated
024	Thumbnail	- Use a boolean instead of a filepath for thumbnail	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR024_Thumbnail.doc	integrated
025	Minor changes	- Minor chnages after implementation	In progress	Not reviewed
026	Removing listener	- Remove invitation listener because there is already Intents	Cancelled			Already part of CR11 with adjustments in CR025
027	Removing Get functions	- Remove GetForIntent methods	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR027_RemovingGetFunctions.doc
028	RCS extensions	- Use metadata instead of Intent filter	Ready for GSMA review	Agreed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR028_RCSExtensions.doc
029	Add geoloc listener	- Add a callback listener for geoloc exchange during chat as for GSh	Cancelled			Cancelled
030	Video share API	- Video sharing API refactoring to internalize the player in the API side	Ready for GSMA review	Not reviewed	https://rcsjta.googlecode.com/git/docs/CR/CR_blackbird_5.2/RCSJTA_TT_BB_CR030_VSH.docx
031	Enumerated types	- Use of enums instead of constants	In progress	Not reviewed
XXX	Exception handling	- Exception handling for any API	Not started	Not reviewed