## Feuille1
CR	Title	Description	Owner	Reviewer	Status	GSMA status
001	Android API	- Missing classes GeolocMessage and Geoloc. / - New RCS 5.2 syntax for feature tag extensions. / - New automata flag in capabilities. / - Missing geoloc methods in the chat service. / - Missing configuration settings for the geoloc service. / - New method to return the service version. / - Remove the altitude in geoloc info. / - Missing chat ID in the file transfer Intent. / - Remove the method transferFileToGroup in the FT API.	JMA	KK	Under review by SONY
002	MM session API	- Internalize the media layer in the API with MSRP support only. / - Remove any SDP parameters in the API definition. / - Rename package to “com.gsma.services.rcs.session”. / - Add new service ID syntax.	JMA	KK	Update CR after new RCS5.2 release
003	Application identification	- Add an application ID to identify the application using the service API. / - Add a method to indicate that it’s an app-to-app service	JMA	KK	Add also appId in database and callback
004	URI for filenames	- Use an Android Uri instead of a String for filenames	JMA	KK	Ready for GSMA review
005	Delete methods	- Add method to delete logs (chat, message, FT, CSH)	KK	PL	Ready for GSMA review
006	Missing Capabilities	- Add a file transfer thumbnail capabilities. / - Add a timestamp	JMA	KK	Under review by SONY
007	Service API	- Add an Intent when service is UP. / - Add methods for service provisioning	JMA	KK	Ready for GSMA review
008	Messaging API	- Few callbacks replaced by intents / - Added intents and/or intent parameters / - isPauseSupported on FileTransfer api / - Resend file or text-message (one2one only)	KK	JMA/PL	Discussions not finalized yet
009	Reason code	- Add a reason code associated to a failure or an aborted status in DB / - Add a reason code in the aborted event listeners.	JMA	KK	Under review by Orange
010	Participant	- Add method to get participant state / - Add listener to get participant state changes	PL	KK	Ready for GSMA review
011	Global listener		KK	JMA/PL	In progress of analysing and writing
012	Read/Displayed/Delivered	- DeliveryInfo provider / - Separate read/unread field / - Delivery status callbacks / - chatID for file transfers / - msgID for file transfers	KK	JMA/PL	Under review by Orange
013	Message search	- Replace BLOB by TEXT for chat messages / - parse content via utility method	PL	KK	Ready for GSMA review
014	Contact Service Utilities	- Add methods to format contact and check validity	KK	JMA	Ready for GSMA review
015	RCS settings	- Add RCS settings / (add comments for MaxMessageLength in chat + GC)	PL	KK	In progress of analysing and writing
016	Display Name	- Add method to get the display name associated to a contact. / - Add column in contact DB	JMA/PL	KK	Currently in review
017	Use case capabilities	- define methods to check capabilities depending on Use Cases	KK	JMA/PL	Not started yet
018	Get/open/accept for chat/gc/ft	- Queuing / - Dequeuing / - Hide rejoin / restart	KK	JMA/PL	Not started yet
019	Undelivered messages				Discussions not finalized yet
020	Merged cursors/EventLogProvider	Pseudo content provider	KK	JMA/PL	Proof of concept in progress by SONY
021	Intents	Pass only ID in Intent parameter and then use the databse provider to extract informations.	KK	JMA	In progress
022	Contact ID object	Define an object ContactId instead of using String for robutness	KK	JMA	In progress
023	JoynUtils	Rename JoynClient by JoynService	JMA	KK	In progress
TBD	Exception handling				Purposly postponed until last